## Summary
 | time axis 2007-05-11 to 2007-07-27
| Fri | 2007-05-14 | 2007-05-15 | 2007-05-16 | 2007-05-17 | 2007-05-18 | 2007-05-21 | 2007-05-22 | 2007-05-23 | 2007-05-24 | 2007-05-25 | 2007-05-28 | 2007-05-29 | 2007-05-30 | 2007-05-31 | 2007-06-01 | 2007-06-04 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-11 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15 | 2007-06-18 | 2007-06-19 | 2007-06-20 | 2007-06-21 | 2007-06-22 | 2007-06-25 | 2007-06-26 | 2007-06-27 | 2007-06-28 | 2007-06-29 | 2007-07-02 | 2007-07-03 | 2007-07-04 | 2007-07-05 | 2007-07-06 | 2007-07-09 | 2007-07-10 | 2007-07-11 | 2007-07-12 | 2007-07-13 | 2007-07-16 | 2007-07-17 | 2007-07-18 | 2007-07-19 | 2007-07-20 | 2007-07-23 | 2007-07-24 | 2007-07-25 | 2007-07-26 | 2007-07-27
Alpha 2.0 | 56.5 | 54.25 | 55 | 53 | 53 | 50 | 47.5 | 45.5 | 38.5 | 33.5 | 29.5 | 29.25 | 27.25 | 28.75 | 21.75 | 18 | 17 | 15 | 10 | 5 | 3 | 3 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alpha 2.1 | 101 | 101 | 101 | 101 | 101 | 101 | 100 | 100 | 98 | 99 | 98.5 | 102.5 | 102.5 | 101.5 | 101.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 101.5 | 101.5 | 100.5 | 100 | 98.5 | 94.5 | 94.5 | 90.5 | 85.5 | 83.5 | 80.5 | 78.5 | 78.5 | 77.25 | 73.75 | 72.25 | 71 | 64 | 59.5 | 57.5 | 52.5 | 51 | 49 | 47.25 | 41 | 38 | 37 | 37 | 35 | 31 | 30 | 32 | 28
Alpha 3.0 | 121.5 | 120.5 | 120.5 | 120.5 | 120.5 | 120.5 | 120.5 | 112.5 | 111.5 | 111.5 | 111.5 | 110.5 | 110.5 | 110.5 | 110.5 | 106.5 | 106.5 | 106.5 | 106.5 | 106.5 | 106.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | 279 | 275.75 | 276.5 | 274.5 | 274.5 | 271.5 | 268 | 258 | 248 | 244 | 239.5 | 242.25 | 240.25 | 240.75 | 233.75 | 225 | 224 | 222 | 217 | 212 | 211 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Alpha 2.0 | 2007-05-11: 56.5; 2007-05-14: 54.25; 2007-05-15: 55; 2007-05-16: 53; 2007-05-17: 53; 2007-05-18: 50; 2007-05-21: 47.5; 2007-05-22: 45.5; 2007-05-23: 38.5; 2007-05-24: 33.5; 2007-05-25: 29.5; 2007-05-28: 29.25; 2007-05-29: 27.25; 2007-05-30: 28.75; 2007-05-31: 21.75; 2007-06-01: 18; 2007-06-04: 17; 2007-06-05: 15; 2007-06-06: 10; 2007-06-07: 5; 2007-06-08: 3; 2007-06-11: 3; 2007-06-12: 7; 2007-06-13: 6; 2007-06-14: 5; 2007-06-15: 0
Vacations | 2007-05-11: 5; 2007-05-14: 5; 2007-05-15: 5; 2007-05-16: 5; 2007-05-17: 5; 2007-05-18: 5; 2007-05-21: 5; 2007-05-22: 5; 2007-05-23: 5; 2007-05-24: 5; 2007-05-25: 5; 2007-05-28: 5; 2007-05-29: 5; 2007-05-30: 5; 2007-05-31: 5; 2007-06-01: 5; 2007-06-04: 5; 2007-06-05: 5; 2007-06-06: 5; 2007-06-07: 5; 2007-06-08: 5; 2007-06-11: 0
Holidays | 2007-05-11: 2; 2007-05-14: 2; 2007-05-15: 2; 2007-05-16: 2; 2007-05-17: 1; 2007-05-18: 0; 2007-05-21: 0; 2007-05-22: 0; 2007-05-23: 0; 2007-05-24: 0; 2007-05-25: 0; 2007-05-28: 0; 2007-05-29: 0; 2007-05-30: 0; 2007-05-31: 0; 2007-06-01: 0; 2007-06-04: 0; 2007-06-05: 0; 2007-06-06: 0; 2007-06-07: 0; 2007-06-08: 0; 2007-06-11: 0; 2007-06-12: 0; 2007-06-13: 0; 2007-06-14: 0; 2007-06-15: 0
Developpers | 2007-05-11: 6; 2007-05-14: 6; 2007-05-15: 6; 2007-05-16: 6; 2007-05-17: 6; 2007-05-18: 6; 2007-05-21: 6; 2007-05-22: 6; 2007-05-23: 6; 2007-05-24: 6; 2007-05-25: 6; 2007-05-28: 6; 2007-05-29: 6; 2007-05-30: 6; 2007-05-31: 6; 2007-06-01: 6; 2007-06-04: 6; 2007-06-05: 6; 2007-06-06: 6; 2007-06-07: 6; 2007-06-08: 6; 2007-06-11: 6; 2007-06-12: 6; 2007-06-13: 6; 2007-06-14: 6; 2007-06-15: 6
Burn Factor | 2007-05-11: 66%; 2007-05-14: 66%; 2007-05-15: 66%; 2007-05-16: 66%; 2007-05-17: 66%; 2007-05-18: 66%; 2007-05-21: 66%; 2007-05-22: 66%; 2007-05-23: 66%; 2007-05-24: 66%; 2007-05-25: 66%; 2007-05-28: 66%; 2007-05-29: 66%; 2007-05-30: 66%; 2007-05-31: 66%; 2007-06-01: 66%; 2007-06-04: 66%; 2007-06-05: 66%; 2007-06-06: 66%; 2007-06-07: 66%; 2007-06-08: 66%; 2007-06-11: 66%; 2007-06-12: 66%; 2007-06-13: 66%; 2007-06-14: 66%; 2007-06-15: 66%
Work days | 2007-05-11: 17.101; 2007-05-14: 16.5328; 2007-05-15: 16.7222; 2007-05-16: 16.2172; 2007-05-17: 15.2172; 2007-05-18: 13.4596; 2007-05-21: 12.8283; 2007-05-22: 12.3232; 2007-05-23: 10.5556; 2007-05-24: 9.2929; 2007-05-25: 8.2828; 2007-05-28: 8.2197; 2007-05-29: 7.7146; 2007-05-30: 8.0934; 2007-05-31: 6.3258; 2007-06-01: 5.3788; 2007-06-04: 5.1263; 2007-06-05: 4.6212; 2007-06-06: 3.3586; 2007-06-07: 2.096; 2007-06-08: 1.5909; 2007-06-11: 0.75758; 2007-06-12: 1.7677; 2007-06-13: 1.5152; 2007-06-14: 1.2626; 2007-06-15: 0
End Date | 2007-05-11: 2007-06-03 22:36; 2007-05-14: 2007-06-06 03:30; 2007-05-15: 2007-06-07 09:52; 2007-05-16: 2007-06-07 16:54; 2007-05-17: 2007-06-07 07:18; 2007-05-18: 2007-06-05 20:15; 2007-05-21: 2007-06-07 23:02; 2007-05-22: 2007-06-08 06:04; 2007-05-23: 2007-06-06 18:40; 2007-05-24: 2007-06-06 00:15; 2007-05-25: 2007-06-05 14:18; 2007-05-28: 2007-06-08 12:11; 2007-05-29: 2007-06-08 19:13; 2007-05-30: 2007-06-10 07:56; 2007-05-31: 2007-06-08 20:33; 2007-06-01: 2007-06-08 12:44; 2007-06-04: 2007-06-11 04:15; 2007-06-05: 2007-06-11 11:16; 2007-06-06: 2007-06-10 16:51; 2007-06-07: 2007-06-09 22:25; 2007-06-08: 2007-06-10 05:27; 2007-06-11: 2007-06-12 01:27; 2007-06-12: 2007-06-14 11:24; 2007-06-13: 2007-06-15 02:55; 2007-06-14: 2007-06-15 18:25; 2007-06-15: 2007-06-15
Alpha 2.1 | 157.5 | 155.25 | 156 | 154 | 154 | 151 | 147.5 | 145.5 | 136.5 | 132.5 | 128 | 131.75 | 129.75 | 130.25 | 123.25 | 118.5 | 117.5 | 115.5 | 110.5 | 105.5 | 104.5 | 104.5 | 107.5 | 106 | 103.5 | 94.5 | 94.5 | 90.5 | 85.5 | 83.5 | 80.5 | 78.5 | 78.5 | 77.25 | 73.75 | 72.25 | 71 | 64 | 59.5 | 57.5 | 52.5 | 51 | 49 | 47.25 | 41 | 38 | 37 | 37 | 35 | 31 | 30 | 32 | 28
Vacations | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Holidays | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developpers | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Burn Factor | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66%
Work days | 52.7273 | 52.0455 | 52.2727 | 51.6667 | 50.6667 | 48.7576 | 47.697 | 47.0909 | 44.3636 | 43.1515 | 41.7879 | 42.9242 | 42.3182 | 42.4697 | 40.3485 | 38.9091 | 38.6061 | 38 | 36.4848 | 34.9697 | 34.6667 | 34.6667 | 35.5758 | 35.1212 | 34.3636 | 31.6364 | 31.6364 | 30.4242 | 28.9091 | 28.303 | 27.3939 | 26.7879 | 24.5879 | 24.2091 | 23.1485 | 22.6939 | 22.3152 | 20.1939 | 18.8303 | 18.2242 | 16.7091 | 16.2545 | 15.6485 | 15.1182 | 13.2242 | 12.3152 | 12.0121 | 12.0121 | 11.4061 | 10.1939 | 9.8909 | 10.497 | 9.2848
End Date | 2007-07-23 19:38 | 2007-07-25 20:44 | 2007-07-27 04:22 | 2007-07-27 08:00 | 2007-07-26 22:24 | 2007-07-25 06:15 | 2007-07-26 18:37 | 2007-07-26 22:15 | 2007-07-24 02:37 | 2007-07-23 09:53 | 2007-07-22 12:04 | 2007-07-27 02:15 | 2007-07-27 05:53 | 2007-07-28 10:59 | 2007-07-26 11:43 | 2007-07-25 11:21 | 2007-07-28 01:10 | 2007-07-28 04:48 | 2007-07-27 01:53 | 2007-07-25 22:59 | 2007-07-26 12:48 | 2007-07-29 12:48 | 2007-07-31 19:21 | 2007-08-01 04:04 | 2007-08-01 02:37 | 2007-07-29 06:59 | 2007-08-01 06:59 | 2007-07-31 14:15 | 2007-07-30 11:21 | 2007-07-30 14:59 | 2007-07-30 08:26 | 2007-08-01 12:04 | 2007-07-30 10:09 | 2007-07-30 21:26 | 2007-07-30 09:47 | 2007-07-30 18:31 | 2007-08-02 05:47 | 2007-07-31 06:31 | 2007-07-30 08:42 | 2007-07-30 12:20 | 2007-07-29 09:26 | 2007-07-31 18:09 | 2007-07-31 21:47 | 2007-08-01 03:58 | 2007-07-30 12:20 | 2007-07-30 05:47 | 2007-08-01 19:36 | 2007-08-02 19:36 | 2007-08-02 23:15 | 2007-08-02 06:31 | 2007-08-02 20:20 | 2007-08-06 16:42 | 2007-08-05 23:58
Alpha 3.0 | 279 | 275.75 | 276.5 | 274.5 | 274.5 | 271.5 | 268 | 258 | 248 | 244 | 239.5 | 242.25 | 240.25 | 240.75 | 233.75 | 225 | 224 | 222 | 217 | 212 | 211 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Vacations | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62
Holidays | bar: 2007-05-11 to 2007-07-24
Developpers | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Burn Factor | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66% | 66%
Work days | 82.2879 | 81.4672 | 81.6566 | 81.1515 | 81.1515 | 80.3939 | 79.5101 | 76.9848 | 74.4596 | 73.4495 | 72.3131 | 73.0076 | 72.5025 | 72.6288 | 70.8611 | 68.6515 | 68.399 | 67.8939 | 66.6313 | 65.3687 | 65.1162 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
End Date | 2007-09-03 04:52 | 2007-09-05 01:18 | 2007-09-06 07:40 | 2007-09-06 14:41 | 2007-09-07 14:41 | 2007-09-07 13:14 | 2007-09-09 07:32 | 2007-09-06 18:41 | 2007-09-04 05:51 | 2007-09-03 19:54 | 2007-09-03 05:43 | 2007-09-07 05:03 | 2007-09-07 12:05 | 2007-09-08 16:20 | 2007-09-07 04:56 | 2007-09-05 02:41 | 2007-09-07 18:12 | 2007-09-08 01:14 | 2007-09-07 06:49 | 2007-09-06 12:23 | 2007-09-07 03:54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Workload
fd | 41.75 | 41.75 | 43.5 | 43.5 | 43.5 | 43.5 | 43.5 | 43.5 | 39.5 | 39.5 | 37.5 | 43.25 | 43.25 | 43.25 | 43.25 | 44.5 | 44.5 | 44.5 | 41.5 | 40.5 | 40.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ac | 58 | 58 | 57.5 | 56.5 | 56.5 | 56.5 | 55.5 | 54 | 53 | 53 | 51 | 50 | 49 | 48 | 41 | 40 | 40 | 40 | 40 | 40 | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
lj | 47.5 | 47.5 | 45 | 44 | 44 | 43 | 42 | 41.5 | 40.5 | 40.5 | 41 | 40 | 40 | 42.5 | 42.5 | 43.5 | 42.5 | 41.5 | 40.5 | 39.5 | 38.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
hc | 42.75 | 41.5 | 40.5 | 40.5 | 40.5 | 38.5 | 37 | 37 | 34 | 34 | 33 | 32 | 32 | 32 | 32 | 30 | 30 | 31 | 31 | 30 | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
gs | 47 | 45 | 45 | 45 | 45 | 45 | 45 | 37 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 28 | 28 | 28 | 28 | 27 | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
pg | 39 | 39 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 38 | 38 | 38 | 37 | 36 | 36 | 36 | 36 | 34 | 33 | 32 | 32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | 276 | 272.75 | 273.5 | 271.5 | 271.5 | 268.5 | 265 | 255 | 245 | 241 | 236.5 | 239.25 | 237.25 | 237.75 | 230.75 | 222 | 221 | 219 | 214 | 209 | 208 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Alpha 2.0 Workload
fd | 2007-05-11: 8.25; 2007-05-14: 8.25; 2007-05-15: 10; 2007-05-16: 10; 2007-05-17: 10; 2007-05-18: 10; 2007-05-21: 10; 2007-05-22: 10; 2007-05-23: 6; 2007-05-24: 6; 2007-05-25: 4; 2007-05-28: 3.75; 2007-05-29: 3.75; 2007-05-30: 3.75; 2007-05-31: 3.75; 2007-06-01: 5; 2007-06-04: 5; 2007-06-05: 5; 2007-06-06: 2; 2007-06-07: 1; 2007-06-08: 1; 2007-06-11: 1; 2007-06-12: 1; 2007-06-13: 1; 2007-06-14: 1; 2007-06-15: 0
ac | 2007-05-11: 15; 2007-05-14: 15; 2007-05-15: 14.5; 2007-05-16: 13.5; 2007-05-17: 13.5; 2007-05-18: 13.5; 2007-05-21: 13.5; 2007-05-22: 12; 2007-05-23: 12; 2007-05-24: 12; 2007-05-25: 10; 2007-05-28: 10; 2007-05-29: 9; 2007-05-30: 8; 2007-05-31: 1; 2007-06-01: 0; 2007-06-04: 0; 2007-06-05: 0; 2007-06-06: 0; 2007-06-07: 0; 2007-06-08: 0; 2007-06-11: 0; 2007-06-12: 3; 2007-06-13: 2; 2007-06-14: 2; 2007-06-15: 0
lj | 2007-05-11: 9.5; 2007-05-14: 9.5; 2007-05-15: 7; 2007-05-16: 6; 2007-05-17: 6; 2007-05-18: 5; 2007-05-21: 4; 2007-05-22: 3.5; 2007-05-23: 2.5; 2007-05-24: 1.5; 2007-05-25: 1.5; 2007-05-28: 1.5; 2007-05-29: 1.5; 2007-05-30: 4; 2007-05-31: 4; 2007-06-01: 5; 2007-06-04: 4; 2007-06-05: 3; 2007-06-06: 2; 2007-06-07: 1; 2007-06-08: 0; 2007-06-11: 0; 2007-06-12: 2; 2007-06-13: 2; 2007-06-14: 1; 2007-06-15: 0
hc | 2007-05-11: 10.75; 2007-05-14: 9.5; 2007-05-15: 8.5; 2007-05-16: 8.5; 2007-05-17: 8.5; 2007-05-18: 6.5; 2007-05-21: 5; 2007-05-22: 5; 2007-05-23: 3; 2007-05-24: 3; 2007-05-25: 3; 2007-05-28: 3; 2007-05-29: 3; 2007-05-30: 3; 2007-05-31: 3; 2007-06-01: 2; 2007-06-04: 2; 2007-06-05: 3; 2007-06-06: 3; 2007-06-07: 2; 2007-06-08: 1; 2007-06-11: 1; 2007-06-12: 0; 2007-06-13: 0; 2007-06-14: 0; 2007-06-15: 0
gs | 2007-05-11: 6; 2007-05-14: 5; 2007-05-15: 5; 2007-05-16: 5; 2007-05-17: 5; 2007-05-18: 5; 2007-05-21: 5; 2007-05-22: 5; 2007-05-23: 5; 2007-05-24: 5; 2007-05-25: 5; 2007-05-28: 5; 2007-05-29: 5; 2007-05-30: 5; 2007-05-31: 5; 2007-06-01: 1; 2007-06-04: 1; 2007-06-05: 1; 2007-06-06: 1; 2007-06-07: 0; 2007-06-08: 0; 2007-06-11: 0; 2007-06-12: 0; 2007-06-13: 0; 2007-06-14: 0; 2007-06-15: 0
pg | 2007-05-11: 7; 2007-05-14: 7; 2007-05-15: 10; 2007-05-16: 10; 2007-05-17: 10; 2007-05-18: 10; 2007-05-21: 10; 2007-05-22: 10; 2007-05-23: 10; 2007-05-24: 6; 2007-05-25: 6; 2007-05-28: 6; 2007-05-29: 5; 2007-05-30: 5; 2007-05-31: 5; 2007-06-01: 5; 2007-06-04: 5; 2007-06-05: 3; 2007-06-06: 2; 2007-06-07: 1; 2007-06-08: 1; 2007-06-11: 1; 2007-06-12: 1; 2007-06-13: 1; 2007-06-14: 1; 2007-06-15: 0
Total | 2007-05-11: 56.5; 2007-05-14: 54.25; 2007-05-15: 55; 2007-05-16: 53; 2007-05-17: 53; 2007-05-18: 50; 2007-05-21: 47.5; 2007-05-22: 45.5; 2007-05-23: 38.5; 2007-05-24: 33.5; 2007-05-25: 29.5; 2007-05-28: 29.25; 2007-05-29: 27.25; 2007-05-30: 28.75; 2007-05-31: 21.75; 2007-06-01: 18; 2007-06-04: 17; 2007-06-05: 15; 2007-06-06: 10; 2007-06-07: 5; 2007-06-08: 3; 2007-06-11: 3; 2007-06-12: 7; 2007-06-13: 6; 2007-06-14: 5; 2007-06-15: 0
Alpha 2.1 Workload
fd | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 22.5 | 21.5 | 20.5 | 20.5 | 20.5 | 17.5 | 16.5 | 16.5 | 15.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 9.5 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ac | 29 | 29 | 29 | 29 | 29 | 29 | 28 | 28 | 27 | 27 | 27 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 26 | 25 | 25 | 25 | 25 | 24 | 23 | 23 | 22 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 9 | 9
lj | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 17.5 | 16.5 | 16.5 | 15.5 | 15.5 | 15.5 | 15.5 | 16 | 15.5 | 15.5 | 14.5 | 13.5 | 13.5 | 12.5 | 12 | 11 | 10.25 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
hc | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 14 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 12 | 12 | 11.5 | 11.5 | 11.5 | 10.5 | 10.5 | 10.5 | 10.5 | 9.5 | 9.5 | 9.25 | 9.25 | 9.25 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4
gs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pg | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 17 | 15 | 15 | 15 | 13 | 13 | 14 | 14 | 11 | 10 | 10 | 9 | 9 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 7 | 7
Total | 101 | 101 | 101 | 101 | 101 | 101 | 100 | 100 | 98 | 99 | 98.5 | 102.5 | 102.5 | 101.5 | 101.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 101.5 | 101.5 | 100.5 | 100 | 98.5 | 94.5 | 94.5 | 90.5 | 85.5 | 83.5 | 80.5 | 78.5 | 78.5 | 77.25 | 73.75 | 72.25 | 71 | 64 | 59.5 | 57.5 | 52.5 | 51 | 49 | 47.25 | 41 | 38 | 37 | 37 | 35 | 31 | 30 | 32 | 28
Alpha 3.0 Workload
fd | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ac | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
lj | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
hc | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
gs | 41 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 27 | 27 | 27 | 27 | 27 | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
pg | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | 118.5 | 117.5 | 117.5 | 117.5 | 117.5 | 117.5 | 117.5 | 109.5 | 108.5 | 108.5 | 108.5 | 107.5 | 107.5 | 107.5 | 107.5 | 103.5 | 103.5 | 103.5 | 103.5 | 103.5 | 103.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Note on AH17: : gregory's vacations musn't be counted here
Note on AH25: : prend en compte les esimations affinees de vacances d'ete plus les jours perdu de lj

## Alpha 2_0
|  | Initial | 2007-02-05 | 2007-02-06 | 2007-02-07 | 2007-02-08 | 2007-02-09 | 2007-02-12 | 2007-02-13 | 2007-02-14 | 2007-02-15 | 2007-02-16 | 2007-02-19 | 2007-02-20 | 2007-02-21 | 2007-02-22 | 2007-02-23 | 2007-02-26 | 2007-02-27 | 2007-02-28 | 2007-03-01 | 2007-03-02 | 2007-03-05 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-09 | 2007-03-12 | 2007-03-13 | 2007-03-14 | 2007-03-15 | 2007-03-16 | 2007-03-19 | 2007-03-20 | 2007-03-21 | 2007-03-22 | 2007-03-23 | 2007-03-26 | 2007-03-27 | 2007-03-28 | 2007-03-29 | 2007-03-30 | 2007-04-02 | 2007-04-03 | 2007-04-04 | 2007-04-05 | 2007-04-06 | 2007-04-09 | 2007-04-10 | 2007-04-11 | 2007-04-12 | 2007-04-13 | 2007-04-16 | 2007-04-17 | 2007-04-18 | 2007-04-19 | 2007-04-20 | 2007-04-23 | 2007-04-24 | 2007-04-25 | 2007-04-26 | 2007-04-27 | 2007-04-30 | 2007-05-01 | 2007-05-02 | 2007-05-03 | 2007-05-04 | 2007-05-07 | 2007-05-08 | 2007-05-09 | 2007-05-10 | 2007-05-11 | 2007-05-14 | 2007-05-15 | 2007-05-16 | 2007-05-17 | 2007-05-18 | 2007-05-21 | 2007-05-22 | 2007-05-23 | 2007-05-24 | 2007-05-25 | 2007-05-28 | 2007-05-29 | 2007-05-30 | 2007-05-31 | 2007-06-01 | 2007-06-04 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-11 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15
Task | Dev. | Dur. | 2007-02-05 | 2007-02-06 | 2007-02-07 | 2007-02-08 | 2007-02-09 | 2007-02-12 | 2007-02-13 | 2007-02-14 | 2007-02-15 | 2007-02-16 | 2007-02-19 | 2007-02-20 | 2007-02-21 | 2007-02-22 | 2007-02-23 | 2007-02-26 | 2007-02-27 | 2007-02-28 | 2007-03-01 | 2007-03-02 | 2007-03-05 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-09 | 2007-03-12 | 2007-03-13 | 2007-03-14 | 2007-03-15 | 2007-03-16 | 2007-03-19 | 2007-03-20 | 2007-03-21 | 2007-03-22 | 2007-03-23 | 2007-03-26 | 2007-03-27 | 2007-03-28 | 2007-03-29 | 2007-03-30 | 2007-04-02 | 2007-04-03 | 2007-04-04 | 2007-04-05 | 2007-04-06 | 2007-04-09 | 2007-04-10 | 2007-04-11 | 2007-04-12 | 2007-04-13 | 2007-04-16 | 2007-04-17 | 2007-04-18 | 2007-04-19 | 2007-04-20 | 2007-04-23 | 2007-04-24 | 2007-04-25 | 2007-04-26 | 2007-04-27 | 2007-04-30 | 2007-05-01 | 2007-05-02 | 2007-05-03 | 2007-05-04 | 2007-05-07 | 2007-05-08 | 2007-05-09 | 2007-05-10 | 2007-05-11 | 2007-05-14 | 2007-05-15 | 2007-05-16 | 2007-05-17 | 2007-05-18 | 2007-05-21 | 2007-05-22 | 2007-05-23 | 2007-05-24 | 2007-05-25 | 2007-05-28 | 2007-05-29 | 2007-05-30 | 2007-05-31 | 2007-06-01 | 2007-06-04 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-11 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15
alpha 1_2 bug fixes
fix 5 | lj | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
fix 4 | hc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
fix 3 | gs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
fix 2 | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
fix 1 | ac | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
flat_place
modify placer initilization | lj |  | 5 | 5 | 4.5 | 0
generate FPL (flat place data) | fd |  | 10 | 10 | 0
update top_shell | lj |  | 2 | 2 | 2 | 0
test and debug | lj |  | 5 | 5 | 5 | 5 | 4 | 1.5 | 1 | 1 | 0
verif (for xa_archi)
generate verification library models | fd | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
generate verification library models | gs | [10 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
update f4_16000 library
generate verification library models | pg | [20 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
update f4_16000 library
adapt to new verification model | gs | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
adapt ZTV plug-in
update timing initialization and annotation
merge libzin in libzan | gs |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
merge libzin in libzan | fd | [33 empty] | 3 | 3 | 0
update the plugin zan
use zan::annotate generic parser code to create zan::initialize
code optimization
add knd policy | pg | [9 empty] | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
separate luts & dffs
copy and update from architecture xa to xb
traits for archi and macro | ac | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
plugin libarctsn | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
plugin libarczin | gs | 5 | 5 | 5 | 0
plugin libarczan | gs | 3 | 3 | 3 | 0
plugin libarcsap | ac | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
plugin libmaczin and libmaczan | gs | 1 | 1 | 1 | 0
plugin libmacmpl | lj | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
builder
either adapt from flexeos or port on repository | fd | 10 | 20 | 20 | 20 | 20 | 20 | 19.5 | 19 | 19 | 18 | 0
equate parser/drivers | fd |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
update top_route | hc | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
update mro::rarch
update MRO file format and parser/driver in libmdf
add plugin for groups routing
update MRO file generator in zarkitek | fd | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
update verif
update verification library model | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
adapt to new verification model | gs | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
test & debug 1 | gs | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
timing analysis invalid memory reference on lark | gs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | [22 empty] | 2 | 2 | 0
test & debug 3 | lj | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
track top_shell randomness | lj | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | [22 empty] | 2 | 2 | 0
generate appropriate ngen data file | pg | [10 empty] | 2 | 2 | 1 | 1 | 0
copy and update from architecture xa to xb | lj | [10 empty] | 1.5 | 1 | 1 | 0.5 | 0
copy and update from architecture xa to xb | fd | [10 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0
plugin libarctsn | lj | [10 empty] | 3 | 3 | 3 | 3 | 3 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 0
update de xb_arch_group_traits
build lut-adder-ff groups
plugin libarcsap | ac | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0
plugin libmacmpl | lj | [10 empty] | 5 | 5 | 5 | 5 | 4.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
builder (adapt from flexeos)
add LUT and FF in architecture | fd | [10 empty] | 1 | 0
enable management | fd | [10 empty] | 5 | 5 | 5 | 5 | 3 | 3 | 0
add buffer on adder entries | fd | [10 empty] | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0
update MRO file generator in zarkitek | pg | [10 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 13 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 0
update top_route | hc | [10 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
update mro::rarch
update MRO file format and parser/driver in libmdf
add plugin for groups routing
update mro::rnetlist and signal router
update verif
update verification library model | gs | [10 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
adapt to new verification model | gs | [10 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
top_route modification specification | hc | [33 empty] | 1 | 1 | 0
autoconstrain
identify clocks, input and output | fd | [20 empty] | 3 | 3 | 2 | 1 | 0
identify and set dummy values for input delay, output delay and clock period.
top_delay
update routing tree traversing to compute delays | hc
export_top_delay
update the KND parser/driver (domain, shadow) | gs | 1 | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
top_shell
documentation for top shell | pg | 1 | [25 empty] | 1 | 1 | 1 | 1 | 0 | 0
Automatic Regression
scripts to run the testcases | ac | [33 empty] | 1 | 1 | 0
scripts to run extract statistics | ac | [33 empty] | 2 | 2 | 0
release
integration, quality & regression | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
alpha 1_2 bug fixes
fix 6 | pg | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
fix 5 | lj | [35 empty] | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0
fix 4 | hc | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.25 | 1.25 | 1.25 | 1.25 | 0
fix 3 | gs | [35 empty] | 2 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0
fix 2 | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0.5 | 0.5 | 0 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
fix 1 | ac | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
netgen
test & integration | pg | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Zarkitek
update MRO file generator in zarkitek
specification | pg | [35 empty] | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0
update MRO file format and parser/driver in libmdf | pg | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0
implementation | pg | [35 empty] | 10 | 10 | 10 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0
libzar utility | fd | [36 empty] | 1 | 0
test & integration | pg | [35 empty] | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 6.5 | 6.5 | 4.5 | 3.5 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Architecture (nice to have)
xc_archi (fisrt real architecture netlist)
specify hard/zarkitek exchange format | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
primitive library description | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
update zarkitek (generate kad + dly + zan) | fd | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
builder
test & integration | fd | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
top_shell
set_design
create groups (plugin libarctsn)
specification with router guys | lj | [35 empty] | 1 | 0
implementation | lj | [35 empty] | 3 | 2.75 | 1.5 | 0 |  |  | 0.25 | 0
update xb_arch_group_traits
build lut-adder-ff groups
test & integration | lj | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.75 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
merge libzin, libzan
implementation | fd | [35 empty] | 1 | 0.25 | 0
test & integration | fd | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
import_flat_route
update duplication (net between lut-dff) | lj | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
nice to have
simplifications (remove hierarchy) | lj | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
zdb2knd with timing | gs | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
update KND parser/driver (domain, shadow) | gs | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
flat_place
update plug-in libxaarcmpl (groups creation) | lj | [35 empty] | 4 | 4 | 4 | 3 | 2 | 1.5 | 1 | 0.25 | 0.25 | 0.5 | 0
update writeback (assign sites to lut and dff) | lj | [35 empty] | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1.5 | 1 | 0
flat_route (separate Lut+Dff)
specification | hc | [35 empty] | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
update mro::rarch | hc | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 0.25 | 0
update mro::rnetlist
implementation | hc | [35 empty] | 5 | 5 | 4 | 3 | 2.5 | 2.5 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.25 | 0.25 | 0
test & integration | hc | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2 | 2 | 2 | 2 | 1.5 | 1.25 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
update plugin
orientate functions
implementation | fd | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1.5 | 1 | 1 | 0.75 | 0
test & integration | fd | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2 | 2 | 1.25 | 2 | 2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
materialize functions
implementation | hc | [35 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9.5 | 9.5 | 9.5 | 9 | 8 | 0
implementation v4x4 | hc | [54 empty] | 5 | 5 | 4.5 | 3 | 2.5 | 4 | 4 | 4 | 4 | 3 | 2 | 1.5 | 1.5 | 1.5 | 0.25 | 0.25 | 0.25 | 0
implementation | fd | 2 | [51 empty] | 1 | 0
implementation vo | lj | 2 | [53 empty] | 3 | 3 | 3 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0
test & integration | hc | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 3 | 1 | 0
test & integration | lj | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 4.5 | 4.5 | 4.5 | 2 | 1 | 1 | 0
flat_route (use bbox to accelerate routing)
specification | hc | [35 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0
update plugin
orientate functions
implementation | fd | [35 empty] | 2 | 2 | 2 | 1.75 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
test & integration | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
signal router
implementation | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
test & integration | fd | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
dump statistics on routing | fd | [72 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 0
move tlm into macro (xa architecture)
update anf | fd | [54 empty] | 0.5 | 0.5 | 0.5 | 0
test & integration | fd | [54 empty] | 1 | 0
arkitek
extended bbox for inout | fd | [57 empty] | 4 | 3.75 | 1 | 0.5 | 0.5 | 0.5 | 0
bbox in mro | fd | [57 empty] | 1 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
test & integration | fd | [57 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
verification
adapt to new verification model (xa_archi)
adapt ZTV plug-in | gs | [35 empty] | 2 | 2 | 2 | 0.5 | 0
test & integration | gs | [35 empty] | 1 | 1 | 1 | 0.5 | 0
update verif (xb_archi)
update verification library model | gs | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
update verification library model | pg | [52 empty] | 1 | 0
adapt to new verification model | gs | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
adapt to new verification model | pg | [53 empty] | 5 | 2 | 2 | 1.25 | 0.75 | 0
simulation with verification model | pg | [58 empty] | 5 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0
simulation with verification model for xb | pg | [72 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0
generate .lib (xa_archi) | gs | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
generate .lib (xb_archi) | gs | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0
S.T.A. validation | gs | [35 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 7.5 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 4 | 3 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
code optimization
knd policy integration | fd | [35 empty] | 1 | 1 | 0.5 | 0
flat_place improvements (cpu) | lj | [35 empty] | 2 | [15 empty] | 2 | 1.25 | 0.25 | 0
test & debug
timing analysis invalid memory reference on lark | gs | [35 empty] | 1 | 1 | 0
Logfile generation (nice to have)
logger specification | ac | [43 empty] | 1 | 1 | 0
library implementation | ac | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
update all libraries messages | ac | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
analysis
place and route satistics specification | ac | [43 empty] | 1 | 0
routing/network
analyze routing quality | ac | [35 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
analyze top network congestion | ac | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
placement
enhance top placer statistics | ac | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
enhance mac placer statistics | lj | [35 empty] | 2 | [15 empty] | 2 | 2 | 2 | 0 | [28 empty] | 1 | 1 | 0
Automatic Regression
scripts to run the test-cases | ac | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
scripts to run statistics extraction | ac | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
release
integration, quality & regression | ac | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | [6 empty] | 3 | 2 | 2 | 0
integration, quality & regression | fd | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3.75 | 3.75 | 3.75 | 3.75 | 5 | 5 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0
integration, quality & regression | gs | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 0
integration, quality & regression | hc | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 0
integration, quality & regression | lj | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 3 | 3 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 2 | 2 | 1 | 0
integration, quality & regression | pg | [35 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Total |  | 104 | 144 | 144 | 129.5 | 123 | 122 | 119 | 118 | 118 | 118 | 100 | 97.5 | 94.5 | 94 | 89.5 | 88.5 | 84 | 83 | 83 | 82 | 81 | 80 | 78 | 75.75 | 73.75 | 73.75 | 74.75 | 74.25 | 73.25 | 73.25 | 72.25 | 72.25 | 72.25 | 78.25 | 78.25 | 190 | 183.25 | 176.75 | 168.5 | 163.75 | 159.75 | 156 | 146.5 | 144 | 138.25 | 133.25 | 133.25 | 131.25 | 129.25 | 126.5 | 121.75 | 119.25 | 117.75 | 110.75 | 99.5 | 98 | 92.75 | 94.75 | 96.25 | 95.5 | 78 | 78 | 78 | 73.25 | 69.25 | 65.75 | 65.75 | 65.75 | 58.75 | 58.75 | 56.5 | 54.25 | 55 | 53 | 53 | 50 | 47.5 | 45.5 | 38.5 | 33.5 | 29.5 | 29.25 | 27.25 | 28.75 | 21.75 | 18 | 17 | 15 | 10 | 5 | 3 | 3 | 7 | 6 | 5 | 0
Note on F11: M2000: completed
Note on F33: M2000: canceled. Depend on update timing completion
Note on F34: M2000: canceled. Depend on update timing completion
Note on F36: M2000: canceled. Depend on update timing completion
Note on F164: M2000: completed
Note on G10: M2000: sudenly, lj declare this task finished. So it's completed.
Note on G12: M2000: sudenly, lj declare this task finished. So it's completed.
Note on G163: M2000: sudenly, lj declare this task finished. So it's completed.
Note on G165: M2000: sudenly, lj declare this task finished. So it's completed.
Note on I13: M2000: debbug done, especialy for adder and ram8k. Testing requires some more work (update top_shell again and performe more tests in bip)
Note on I39: M2000: task activated
Note on I166: M2000: debbug done, especialy for adder and ram8k. Testing requires some more work (update top_shell again and performe more tests in bip)
Note on L28: M2000: this will ease and securise the task alpha_2_0::A24. it dosent depend on any task. Task alpha_2_0::A24 must start after completion of this task
Note on M16: M2000: transfered from alpha_2_0:A15
Note on M20: M2000: reevaluated after simplification
Note on M31: M2000: transfered bellow
Note on M32: M2000: transfered bellow
Note on M35: M2000: transfered bellow
Note on M37: M2000: transfered bellow
Note on M39: M2000: transfered bellow
Note on M40: M2000: transfered bellow
Note on M41: M2000: transfered bellow
Note on M45: M2000: transfered bellow
Note on M47: M2000: transfered bellow
Note on M48: M2000: transfered bellow
Note on M49: M2000: transfered bellow
Note on M50: M2000: transfered bellow
Note on M51: M2000: transfered bellow
Note on M52: M2000: transfered bellow
Note on M53: M2000: the actual update of the file should be done by Olivier's team. This 2 days are just a placeholder (social engeneering).
Note on M180: M2000: transfered from alpha_2_0:A15
Note on M188: M2000: reevaluated after simplification
Note on M192: M2000: transfered bellow
Note on M193: M2000: transfered bellow
Note on N54: Ludo: Standby waitting for ngen data file
Note on W16: Jean-Sebastien Weil: remaining transfered to pg
Note on AJ23: fd: task moved to fd
Note on AJ50: Jean-Sebastien Weil: bug tracking on alpha 1.2
Note on AJ52: Jean-Sebastien Weil: bug tracking on alpha 1.2
Note on AL4: Jean-Sebastien Weil: Canceled
Note on AL5: Jean-Sebastien Weil: Canceled
Note on AL6: Jean-Sebastien Weil: Canceled
Note on AL7: Jean-Sebastien Weil: Canceled
Note on AL8: Jean-Sebastien Weil: Canceled
Note on AL18: Jean-Sebastien Weil: Canceled
Note on AL20: Jean-Sebastien Weil: Canceled
Note on AL24: Jean-Sebastien Weil: Canceled
Note on AL28: Jean-Sebastien Weil: Canceled
Note on AL50: Jean-Sebastien Weil: Canceled
Note on AL52: Jean-Sebastien Weil: Canceled
Note on AL55: Jean-Sebastien Weil: Canceled
Note on AL56: Jean-Sebastien Weil: Canceled
Note on AL59: Jean-Sebastien Weil: Canceled
Note on AL60: Jean-Sebastien Weil: Canceled
Note on AL65: Jean-Sebastien Weil: Canceled
Note on AL66: Jean-Sebastien Weil: Canceled
Note on AL72: Jean-Sebastien Weil: Canceled
Note on AL73: Jean-Sebastien Weil: Canceled
Note on AL74: Jean-Sebastien Weil: Canceled
Note on AL81: Jean-Sebastien Weil: Canceled
Note on AL85: Jean-Sebastien Weil: Canceled
Note on AL86: Jean-Sebastien Weil: Canceled
Note on AL88: Jean-Sebastien Weil: Canceled
Note on AM127: Jean-Sebastien Weil: the task was duplicated in march 26 backlog and hence improperly updated.
Note on AS96: ac: fixed bug reported by Bugra on 03/23/2007
Note on AU138: ludo: add lut+dff duplication
Note on BB130: ludo: this feature is not required anymore
Note on BC182: pg: transfered to pg
Note on BD184: pg: transfered to pg
Note on BE133: ludo: cancelled
Note on BE152: Jean-Sebastien Weil: splitted between hc and lj
Note on BE211: ludo: Cancelled
Note on BI186: Jean-Sebastien Weil: new task. Simulate all verification model + at least, one P&R netlist.
Note on BI187: Jean-Sebastien Weil: new task. Simulate all verification model + at least, one P&R netlist.
Note on BJ155: ludo: Underestimated
Note on BK91: Jean-Sebastien Weil: bug fixes will now be loggued appart from the backlog remaining workload
Note on BK92: Jean-Sebastien Weil: bug fixes will now be loggued appart from the backlog remaining workload
Note on BK93: Jean-Sebastien Weil: bug fixes will now be loggued appart from the backlog remaining workload
Note on BK111: Jean-Sebastien Weil: transfered to Alpha 3_0
Note on BK112: Jean-Sebastien Weil: transfered to Alpha 3_0
Note on BK113: Jean-Sebastien Weil: transfered to Alpha 3_0
Note on BK134: Jean-Sebastien Weil: transfered to Alpha 3_0
Note on BK135: Jean-Sebastien Weil: transfered to Alpha 3_0
Note on CH211: ludo: Display stats in lst format
Note on CH222: ludo: try to make all (or most of all) benches to work
Note on CJ222: ludo: Improve evaluators in mac_place

## Alpha 2_1
|  | Initial | 2007-05-04 | 2007-05-07 | 2007-05-08 | 2007-05-09 | 2007-05-10 | 2007-05-11 | 2007-05-14 | 2007-05-15 | 2007-05-16 | 2007-05-17 | 2007-05-18 | 2007-05-21 | 2007-05-22 | 2007-05-23 | 2007-05-24 | 2007-05-25 | 2007-05-28 | 2007-05-29 | 2007-05-30 | 2007-05-31 | 2007-06-01 | 2007-06-04 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-11 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15 | 2007-06-18 | 2007-06-19 | 2007-06-20 | 2007-06-21 | 2007-06-22 | 2007-06-25 | 2007-06-26 | 2007-06-27 | 2007-06-28 | 2007-06-29 | 2007-07-02 | 2007-07-03 | 2007-07-04 | 2007-07-05 | 2007-07-06 | 2007-07-09 | 2007-07-10 | 2007-07-11 | 2007-07-12 | 2007-07-13 | 2007-07-16 | 2007-07-17 | 2007-07-18 | 2007-07-19 | 2007-07-20 | 2007-07-23 | 2007-07-24 | 2007-07-25 | 2007-07-26 | 2007-07-27
Task | Dev. | Dur. | 2007-05-04 | 2007-05-07 | 2007-05-08 | 2007-05-09 | 2007-05-10 | 2007-05-11 | 2007-05-14 | 2007-05-15 | 2007-05-16 | 2007-05-17 | 2007-05-18 | 2007-05-21 | 2007-05-22 | 2007-05-23 | 2007-05-24 | 2007-05-25 | 2007-05-28 | 2007-05-29 | 2007-05-30 | 2007-05-31 | 2007-06-01 | 2007-06-04 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-11 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15 | 2007-06-18 | 2007-06-19 | 2007-06-20 | 2007-06-21 | 2007-06-22 | 2007-06-25 | 2007-06-26 | 2007-06-27 | 2007-06-28 | 2007-06-29 | 2007-07-02 | 2007-07-03 | 2007-07-04 | 2007-07-05 | 2007-07-06 | 2007-07-09 | 2007-07-10 | 2007-07-11 | 2007-07-12 | 2007-07-13 | 2007-07-16 | 2007-07-17 | 2007-07-18 | 2007-07-19 | 2007-07-20 | 2007-07-23 | 2007-07-24 | 2007-07-25 | 2007-07-26 | 2007-07-27
zarkitek
compute statistics value in zarkitek | pg | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
add wire type & compute statistics
delay evaluator enhancement | pg | [57 empty] | 3 | 3
update sap generator | pg | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
update adl grammar
compute data
drive data
update mpl generator | pg | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 0
update adl grammar
compute data
drive data
update mro generator | pg | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
create kat generator | fd | [17 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 2.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
path types
cell port types
delay types
update adl grammar
modify zarkitek
tester and integration
top_shell
zdb2knd with timing
implementation | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
test & integration | fd | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
data base
libknd
implementation | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
update KND parser/driver (domain, shadow)
add bidirectionnal support
slack ratio
synchronise
test & integration | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 0
top_place
delay evaluator | ac | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
update sap parser.driver
update delay while clustering | ac | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
cost functions | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
test & integration | ac | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
flat_place
add mpl timing data in adl (archi xb) | lj | [40 empty] | 0.5 | 0
merge delay code from old placer (flexeos) | lj | [15 empty] | 1 | 0.5
delay evaluator | lj | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 1.5 | 0.5 | 0.5 | 0
update parch / plugin interface
update mpl parser.driver
update delay while clustering | lj | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0
cost functions | lj | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 4 | 4 | 3 | 2.5 | 1.5 | 0.75 | 0
test & integration | lj | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
flat_route
retreive delays from architecture | hc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
update mro::rarch
implementation | hc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0
modify initialisation
introduce signal sort by criticality
modify stack and stack sort function
modify wire cost function
test & integration | hc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 0
bbox integration | fd | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0
use kat path types in plugin | fd | [17 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
replace path_type function
simplify distance function
test & integration
dump routing trees to ascii file | hc | [26 empty] | 1 | 1 | 0 | [9 empty] | 0.25 | 0
release
integration, quality & regression | ac | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
integration, quality & regression | fd | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
integration, quality & regression | hc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
integration, quality & regression | lj | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
integration, quality & regression | pg | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Total |  | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 100 | 100 | 98 | 99 | 98.5 | 102.5 | 102.5 | 101.5 | 101.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 101.5 | 101.5 | 100.5 | 100 | 98.5 | 94.5 | 94.5 | 90.5 | 85.5 | 83.5 | 80.5 | 78.5 | 78.5 | 77.25 | 73.75 | 72.25 | 71 | 64 | 59.5 | 57.5 | 52.5 | 51 | 49 | 47.25 | 41 | 38 | 37 | 37 | 35 | 31 | 30 | 32 | 28
Workload
ac |  | 29 | [36 empty] | 25 | 25 | 24 | 23 | 23 | 22 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 9 | 9
fd |  | 16 | [36 empty] | 15.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 9.5 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
gs |  | 0 | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hc |  | 16 | [36 empty] | 9.5 | 9.5 | 9.25 | 9.25 | 9.25 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4
lj |  | 19 | [36 empty] | 15.5 | 15.5 | 15.5 | 16 | 15.5 | 15.5 | 14.5 | 13.5 | 13.5 | 12.5 | 12 | 11 | 10.25 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
pg |  | 21 | [36 empty] | 13 | 14 | 14 | 11 | 10 | 10 | 9 | 9 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 7 | 7
Total |  | 101 | [36 empty] | 78.5 | 78.5 | 77.25 | 73.75 | 72.25 | 71 | 64 | 59.5 | 57.5 | 52.5 | 51 | 49 | 47.25 | 41 | 38 | 37 | 37 | 35 | 31 | 30 | 32 | 28
Note on AN52: ludo: Standby waitting for knd timing arkitek timing datas
Note on AN53: ludo: Standby waitting for knd timing arkitek timing datas
Note on AN54: ludo: Standby waitting for knd timing arkitek timing datas
Note on AO52: ludo: Standby waitting for knd timing arkitek timing datas
Note on AO53: ludo: Standby waitting for knd timing arkitek timing datas
Note on AO54: ludo: Standby waitting for knd timing arkitek timing datas
Note on AP52: ludo: Standby waitting for knd timing arkitek timing datas
Note on AP53: ludo: Standby waitting for knd timing arkitek timing datas
Note on AP54: ludo: Standby waitting for knd timing arkitek timing datas
Note on AQ52: ludo: Standby waitting for knd timing
Note on AQ53: ludo: Standby waitting for knd timing
Note on AQ54: ludo: Standby waitting for knd timing
Note on AQ59: ludo: Standby waitting for knd timing
Note on AQ64: ludo: Standby waitting for knd timing
Note on AR52: ludo: Standby waitting for knd timing
Note on AR53: ludo: Standby waitting for knd timing
Note on AR54: ludo: Standby waitting for knd timing
Note on AS52: ludo: Standby waitting for knd timing
Note on AS53: ludo: Standby waitting for knd timing
Note on AS54: ludo: Standby waitting for knd timing
Note on AT28: : incorporated in global integration at the end of the cycle
Note on BA54: ludo: waitting for realistic delays for xb archi
Note on BB54: ludo: standby waitting for realistic delays for xb archi

## Alpha 3_0
summary | Task | Owner | Dur. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | milestone | Alpha 3_0
architecture > xc_archi | xc_archi | [28 empty] | Alpha 3_0
architecture > xc_archi > introduce register file | introduce register file | [28 empty] | Alpha 3_0
architecture > xc_archi > introduce 18K ram | introduce 18K ram | [28 empty] | Alpha 3_0
architecture > xc_archi > modify io blocs | modify io blocs | [28 empty] | Alpha 3_0
architecture > xc_archi > primitive library description | primitive library description | [28 empty] | Alpha 3_0
architecture > xc_archi > update lgen | update lgen | fd | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | Alpha 3_0
architecture > xc_archi > update netgen | update netgen | fd | 0 | [26 empty] | Alpha 3_0
architecture > xc_archi > update adl (generate kad + dly + zan) | update adl (generate kad + dly + zan) | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Alpha 3_0
architecture > xc_archi > modify traits | modify traits | fd | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Alpha 3_0
architecture > test & integration | test & integration |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Alpha 3_0
architecture > test & integration > update lgen | update lgen | pg | [27 empty] | Alpha 3_0
architecture > test & integration > update netgen | update netgen | pg | [27 empty] | Alpha 3_0
architecture > test & integration > update adl (generate kad + dly + zan) | update adl (generate kad + dly + zan) | pg | [27 empty] | Alpha 3_0
architecture > test & integration > modify traits | modify traits | pg | [27 empty] | Alpha 3_0
architecture > test & integration > update delay estimator for register file (adl) | update delay estimator for register file (adl) | pg | [27 empty] | Alpha 3_0
architecture > test & integration | test & integration | [28 empty] | Alpha 3_0
architecture > test & integration > update lgen | update lgen | fd | [27 empty] | Alpha 3_0
architecture > test & integration > update netgen | update netgen | fd | [27 empty] | Alpha 3_0
architecture > test & integration > update adl (generate kad + dly + zan) | update adl (generate kad + dly + zan) | fd | [27 empty] | Alpha 3_0
architecture > test & integration > modify traits | modify traits | fd | [27 empty] | Alpha 3_0
architecture > test & integration | test & integration | [28 empty] | Alpha 3_0
architecture | [29 empty] | Alpha 3_0
zarkitek | zarkitek | [28 empty] | Alpha 3_0
zarkitek > time scale adjustment | time scale adjustment | pg | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
zarkitek > time scale adjustment | [29 empty] | Alpha 3_0
builder | builder | [28 empty] | Alpha 3_0
builder > introduce 18K ram | introduce 18K ram | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Alpha 3_0
builder > introduce regiser file | introduce regiser file | fd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Alpha 3_0
builder > test & integration | test & integration | fd | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Alpha 3_0
builder > test & integration | [29 empty] | Alpha 3_0
flat_place | flat_place | [28 empty] | Alpha 3_0
flat_place > dpram18k & register file in plugin | dpram18k & register file in plugin | lj | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
flat_place > test & integration | test & integration | lj | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
flat_place | [29 empty] | Alpha 3_0
flat_route | flat_route | [28 empty] | Alpha 3_0
flat_route > dpram18k & register file integration | dpram18k & register file integration | [28 empty] | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin | update plugin | [28 empty] | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > orientate functions | orientate functions | [28 empty] | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > orientate functions > implementation | implementation | hc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > orientate functions > test & integration | test & integration | hc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > materialize functions | materialize functions | [28 empty] | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > materialize functions > implementation v4x4 | implementation v4x4 | hc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Alpha 3_0
flat_route > dpram18k & register file integration > update plugin > materialize functions > test & integration | test & integration | hc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Alpha 3_0
flat_route | [29 empty] | Alpha 3_0
verification | verification | [28 empty] | Alpha 3_0
verification > 18K ram & regfile integration | 18K ram & regfile integration | [28 empty] | Alpha 3_0
verification > 18K ram & regfile integration > update verilog model | update verilog model | pg | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
verification > 18K ram & regfile integration > simulation with verification model | simulation with verification model | pg | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Alpha 3_0
verification > 18K ram & regfile integration > update timming model (.lib) | update timming model (.lib) | gs | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
verification > 18K ram & regfile integration > update pluging ztv | update pluging ztv | gs | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Alpha 3_0
Alpha 3_0
timing annalysis | timing annalysis | [28 empty] | Alpha 3_0
timing annalysis > enable_asynchonous_reset | enable_asynchonous_reset | gs | 0 | [26 empty] | Alpha 3_0
timing annalysis > asynchonous_path_domain | asynchonous_path_domain | gs | 0 | [26 empty] | Alpha 3_0
timing annalysis > constrain | constrain | [28 empty] | Alpha 3_0
timing annalysis > constrain > generated_clock | generated_clock | gs | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Alpha 3_0
timing annalysis > exception | exception | [28 empty] | Alpha 3_0
timing annalysis > exception > subgraph extraction (no -through) | subgraph extraction (no -through) | gs | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | Alpha 3_0
timing annalysis > exception > false paths | false paths | gs | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | Alpha 3_0
timing annalysis > exception > false path documentation | false path documentation | gs | [27 empty] | Alpha 3_0
timing annalysis > exception > multicycle paths | multicycle paths | gs | [27 empty] | Alpha 3_0
timing annalysis > exception > min/max delay | min/max delay | gs | [27 empty] | Alpha 3_0
timing annalysis > transfer sdc a.p.i to top_shell | transfer sdc a.p.i to top_shell | lj | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Alpha 3_0
timing annalysis > transfer sdc a.p.i to top_shell | transfer sdc a.p.i to top_shell | gs | [27 empty] | Alpha 3_0
timing annalysis > add command | add command | gs | 0 | [26 empty] | Alpha 3_0
timing annalysis > add command > get_pins | get_pins
timing annalysis > add command > get_ports | get_ports
timing annalysis > add command > get_cells | get_cells
timing annalysis > add command > get_clocks | get_clocks
timing annalysis > add command > get_nets | get_nets
timing annalysis > test & integration | test & integration | gs | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
timing annalysis
Optimization | Optimization
Optimization > clusterization | clusterization | ac | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Optimization > clusterization | clusterization | lj | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Optimization > clusterization
release | release
release > integration, quality & regression | integration, quality & regression | ac | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release > integration, quality & regression | integration, quality & regression | fd | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release > integration, quality & regression | integration, quality & regression | gs | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release > integration, quality & regression | integration, quality & regression | hc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release > integration, quality & regression | integration, quality & regression | lj | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release > integration, quality & regression | integration, quality & regression | pg | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
release
release > Total | Total |  | 121.5 | 121.5 | 121.5 | 121.5 | 121.5 | 121.5 | 121.5 | 120.5 | 120.5 | 120.5 | 120.5 | 120.5 | 120.5 | 112.5 | 111.5 | 111.5 | 111.5 | 110.5 | 110.5 | 110.5 | 110.5 | 106.5 | 106.5 | 106.5 | 106.5 | 106.5 | 106.5
Workload | Workload
ac | ac |  | 14
fd | fd |  | 17.5
gs | gs |  | 41
hc | hc |  | 16
lj | lj |  | 19
pg | pg |  | 11
Total | Total |  | 118.5
Total Workload | Total Workload
ac | ac |  | 43
fd | fd |  | 33.5
gs | gs |  | 41
hc | hc |  | 32
lj | lj |  | 38
pg | pg |  | 32
Total | Total |  | 219.5
Note on D8: M2000: postponed : real netlist should be delivered by mid June
Note on D54: M2000: postponed for this release
Note on D55: M2000: postponed for this release
Note on D59: M2000: reduced of 5 day thanks to no -through support
Note on D66: M2000: postponed for this release

## Support & Debug
Task | Started | Elapsed
Arnaud
<task 1>
<task 2>
Antoine
<task 1>
<task 2>
Francois
bug fix alpha 2.0 | 2007-06-28 | 1
bug fix alpha 2.0 | 2007-06-29 | 0.75
<task 2>
Gregory
bug fix alpha 2.1 : add events of the clock path in the clock domain | 2007-07-12 | 0.5
bug fix alpha 2.1 : don't report path from clock port to clock pin of RAM | 2007-07-13 | 0.5
alpha 2.1 : add stats in the report (depth of the worst path) | 2007-07-13 | 0.25
Hugo
architecture checker | 2007-07-03 | 4978
<task 2>
Jean-Sebastien
<task 1>
<task 2>
Ludovic
<task 1>
<task 2>
Pascal
<task 1>
<task 2>
Formulas:
Elapsed = NETWORKDAYS([Started],TODAY())